## Cover
EuroBank
ATTACHMENT 9-A
Projects List
Attachment to Exhibit 9 (In-Flight Projects)

## LAN Projects
Discretionair
Portfolio name | Country | project name | startdate | enddate | status
Innovation and std | NL | WiFi first pilot in Acanthus | may 2006 | 2006-09-01 | ready
Innovation and std | NL | WiFi phase 2: roll out wifi in 2 buildings | Q4 2006 | Q2 2007 | waiting for final decision
Legacy | B | Get rid of Large VLANs CSM/MX | 2007 |  | on the MTP for 2007
Sourcing | NL | make a split between LAN and WAN components | Q4 2006 | Q2 2007 | not started
and functions in the building blocks
Customer
Portfolio name | Country | project name | startdate | enddate | status
Customer FM | NL | new building Laanderpoort Amsterdam ZO | july 2006 | Q1 2007 | execution
Customer FM | NL | Haarlemmerweg bouwdeel 4 | Q1 2007 | ? | is being prepared
Customer RVS | NL | investigate performance problems LAN RVS Ede | Q4 2006 | Q4 2006
Customer RVS | NL | upgrade LAN RVS Ede | 2007
Baseline
| Country | Activity | startdate | enddate | status
LCM | NL+B | Selection new access layer | 2006-04-01 | Q4 2006 | exe
LCM | NL | Roll out new LAN Building Block release. | 2007 |  | not started
LCM | NL | Replace LAN equipment that reaches in 2007 | 2007 |  | not started
end of support status
LCM | B | IP adress changes in National network | 2007 |  | exe
LCM | NL+B | QoS | 2006 | 2006 | ongoing
LCM | NL+B | Multi cast | 2007 | 2007 | ongoing
LCM | B | Obsolete LAN devices in CSM/MX LAN +data center | 2006 |  | exe
LCM | B | Obsolete LAN devices in belgian branches | 2006 |  | exe
LCM | B | Obsolete LAN devices in belgian subsidaries | 2006 |  | exe
Author: Marjan Pie
OpsT Infra ECI BE INE team LanWan
Version: September 2006

## EuroBank-Requested Projects
Nr | Project name | Project Description | High Level project activities | startdate | expected to end | remarks/status
1 | Datacenter-based HW renewal due to depreciation | Renew solution based on the current standard for HW and SW due to depreciation of HW | - Purchase HW/SW - Deploy - Decomission old |  |  | ongoing
2 | Maintain office telephony | Replace depreciated and not performing office telephony and call logging equipment with the current standard. Upgrade capacity meeting growing demand. Improve quality of GSM coverage | - purchase new equipment - change management - decomission the old equipment | q1 | q4 | on schedule
a | Phase out old equipment Nortel Haarlemmerweg | Old releases of PABX's some only best effort | change
b | Phase out old equipment Nortel Leeuwarden, Arnhem and branchoffices(40) | Old releases of PABX's some only best effort | change
c | Phase out old equipment Alcatel Leeuwarden and Haarlemmerweg | Old releases of PABX's some only best effort | change
d | Phase out old equipment Philips ZT WP ( incl Sittard/Arnhem connect to HP/DP) | Releases Old | change
e | Upgrade Ericsson ( CO, TP, CB, IH, OL) incl strovo. Replacement Maintenenance equipment, PC Switches, IP Server MX one | maintenance or support issues and phase out fona network | change
f | TABS = cost/fraude management Ericsson One Box = Voice mail system Ericsson Calacsy= cost/fraude management Avaya | capacity licensies and hand set/ Calacsy in trusted EuroBank LAN and consquence upgrade Ericsson and Avaya | change
g | SRP | strategic space plan FM requirements
h | Upgrade voice logging systems | Upgrade voiceloggers 8,5 and lower to 8,9 and new customers | change
i | Expansion on Voice loggers | expansion of new users | change
j | Upgrade SC Hypotheken | Upgrade SCH environment, because the AnyWAN ATM service is discontinued by NSI. Instead of ATM OC3, IP connectivity will be used to connect to the remotev gateways | change
k | Implementation Vodafone Wireless Office | This can be used as a substitute for a PBX. GSM telephony in stead of fixed telephony. Functionalities like call transfer, conference call, zero rate "internal calling" are already possible. A pilot in EuroBank building "Wilgenplas" will be perfect because of | Change
3 | Server OS versions upgrade | Migrate Wintel servers to the current release | Change | q1 | q4 | controlled within ITT Progam outside SWS, WPS delivers capacity
4 | Server Windows OS major changes | Major changes to the windows server OS affecting applications running on top | - Release |  |  | ongoing
5 | Office-based computer HW renewal due to depreciation | Renew solution based on the current standard for HW and SW due to depreciation of HW | - Purchase HW/SW - Deploy - Decomission old |  |  | ongoing
6 | Workstation Windows OS major changes | Major changes to the workstation OS affecting applications running on top | - Release |  |  | ongoing
7 | Develop collaboration service | Develop as an integral service such new features as: my site, live meetings, instant messaging, web conferencing, web-based files sharing. Decommission old products (Include in Colaboration PAL) | - Research - Development - Backbone deployment - Decomission old infra | q1 | q4 / q1-07 | on schedule
a | Develop collaboration service | Develop as a set of of services such new features as: my site, live meetings, instant messaging, web conferencing, web-based files sharing, etc based on MS suite of products (Sharepoint, live communication server, etc.). Decommission competing IBM product
b | Remote access to Collaboration functionality - technical | Investigation of new technology and pilot (if valid business case or sponsor) | Research Development
c | Implementation of SharePoint broader access | Acceptance by operational departments - Need decision by MT Workplace for using available technology to improve search site, topology and navigation. Goal: grant CEDS users access to Sharepoint Portal environment. | Research Development Backbone deployment
d | Implementation of SharePoint MySite | Acceptance by operational departments - Provide a personal site with a link of the CEDS "home folder" to the MySite-location (parallel the phase-out project of file-and-print/Novell servers). Goal: Link Private Documents view of MySite (SharePoint Portal) | Research Development Backbone deployment
e | Implementation of Office Communicator within CEDS | Specification, architecture, development and acceptance by operational departments - Needed for connection to Live Communication server, will replace Windows Messenger 5.1. | Research Development Backbone deployment
f | Evaluation Lotus Team Workplace/Sametime | Evaluate Lotus Team Workplace/Sametime in relation to Sharepoint/Live Communication server | Research
g | Research replacement file-shares with Sharepoint | Consider Sharepoint for the standard file-sharing solution | Research
h | Implementation streaming media (NL/BE) | Enabling Multicast functionality within EuroBank network Implementing streamingmedia server/webserver Service development | Research Development Backbone deployment
i | Upgrade test environment
j | Improve testenvironment for collaboration | New testserver for investigating | Research Development
k | Cross-forest Authentication Active Directory for SharePoint. Big dependency with directory projects. | Investigation of new technology and pilot (if valid business case or sponsor) - needed for EuroBank broad access to Sharepoint environment, making it cross forest available | Research
8 | Redesign Active Directory | AD is quickly becoming a dominant directory service within EuroBank. original design does not cover current functional, performance and organisational requirements. | - Research - Development - Backbone deployment | q3 | q1/07 | not started
a | Microsoft ADFS | More and more work will/can be outsourced to external parties. Trust relationships must be made on legal, organisational but also on al technical base. | Research
b | Microsoft ADFS | More and more work will/can be outsourced to external parties. Trust relationships must be made on legal, organisational but also on al technical base. | Development
c | Microsoft ADFS | More and more work will/can be outsourced to external parties. Trust relationships must be made on legal, organisational but also on al technical base. | Backbone deployment / Change
d | Redisign AD Infrastructure | redisigne logical model and technical infrastructure | Research / Development
e | Redisign AD Infrastructure | redisigne logical model and technical infrastructure | Backbone deployment / Change
f | Redesign Security Model AD | Tighten security, implement better delegation model | Research / Development
g | Implement new/enhanced Security Model AD | Tighten security, implement better delegation model | Backbone deployement / Change
h | Multi Forest Strategy | Publish strategy for Multi-Forest implementations | Research
i | Research on AD Zoning | Reduce risk of global wide change errors | Research
j | Develop AD Zoning | Reduce risk of global wide change errors | Development
k | Implementation AD Zoning | Reduce risk of global wide change errors | Backbone deployment / Change
l | Enhanced authentication | Investigation on all posibilities to Enhance User/system authentication. (kerberos, strong authentication, Corporate Key Login, special accounts) | Research
m | Enhanced authentication | Investigation on all posibilities to Enhance User/system authentication. (kerberos, strong authentication, Corporate Key Login, special accounts) | Development
n | Enhanced authentication | Investigation on all posibilities to Enhance User/system authentication. (kerberos, strong authentication, Corporate Key Login, special accounts) | Backbone deployment / Change
o | Cross-forest Authentication Active Directory for SharePoint. Big dependency with directory projects. | Investigation of new technology and pilot (if valid business case or sponsor) - needed for EuroBank broad access to Sharepoint environment, making it cross forest available | Research
9 | NetIQ fase 2 | Develop and deploy security monitoring and management tooling for AD. | -Research - Develop - Deploy/upgrade central infra | q3 | q4 | started, fase 1 ended
a | Make AD Tooling more Mature | Recent incidents in the infrastructure showed some lacunas in the used tools. Processes and tooling must be made uniform (not personal). We have to make parts more Pro-Active and it must be possible to make health-snapshots. | Research/ Development/Change
10 | Develop services on CIA levels 3 | Customers are requesting security and availability levels which are higher then the current standard for workplace (C2I2A2). Achieving higher levels requires changes in technology, procedures and possibly organisation | - Develop - Implement - Deploy backbone | q3 | q4/q1-07 | on schedule
11 | Central Backbone upgrade (WPS) | Upgrade capacity or renew hardware/sw or change placement of key centralised infra in order to meet performance and functional demands | Upgrade Blackberry Browse, Remote access infra, video bridge, sharepoint infra. - Renew hw for AD and Corporate directory - Relocate browse infra following datacentres policy | q1 | q4/q1-07 | done within baseline, lcm base
a | Deploy extended Capacity on BlackBerry Enterprise Server | Current BlackBerry environment is capable to serve 500 BlackBerry subscriptions. Next year we estimate to pass this number, so capacity extension is necessary. | Change
b | Upgrade browse infra | Provide for additional capacity meeting rising demand; separate business and workplace infra ensuring needed performance for business applications; optimise hosting of elements (PAC files); follow datacenter policy for browse infra placement (Arnhem or Br | research / Develop / backbone deployment
c | general update | General capacity update (Internet bandwidth included) | Development;
d | general update | General capacity update (Internet bandwidth included) | backbone deployment
e | Update logging facilities | update logging: - storage - reporting - analyse | Research;
f | Update logging facilities | update logging: - storage - reporting - analyse | backbone deployment
g | Implementation of PAC file webservers | Move PAC files from Proxy servers to alternate infrasture/location | Development
h | Implementation of PAC file webservers | Move PAC files from Proxy servers to alternate infrasture/location | Backbone deployment
i | Implementation of PAC file webservers | Move PAC files from Proxy servers to alternate infrasture/location | Release
j | RAS capacity upgrade | General capacity update (Internet bandwidth included) | Development / backbone deployment
k | general update | General capacity update (Internet bandwidth included) | Development
l | general update | General capacity update (Internet bandwidth included) | backbone deployment
12 | Secure File Storage | File archiving for Sox Compliance. Personal file archiving (Home directory) | - Development of the standard solution - Deployment of additional storage capacity - Change on all wintel file servers | q2 | q4 | base ready, interference with INFRA project
a | Archiving | File archiving for Sox Compliance. Personal file archiving (Home directory) | Development, change
b | Archiving Files | File archiving (Home directory and Group directory) | Development, change
c | Legal mail archiving | Implement legal archiving for SOX compliance | change
d | Implement personal archiving | Move PST files to arhiving solution and enable personal archiving | For 2006: Change Implementation of user based archiving (PST files)
e | Maintenance costs of KVS licenses 2006 + extension of KVS licenses SWE | Maintenance costs should be paid for KVS support in 2006. Also new licenses are necessary + maintenance for implementating KVS in SWE. | Baseline
f | Secure e-mail service for encrypted and siging e-mail messages | Based on EuroBank PKI certificates a new service will be setup for enctyped and signing e-mail messages | Development and Implement
g | Develop and implement seperate secure e-mail environment | Setup for a special group of users (EuroBank House, IIM and CF&R) a separate secure e-mail environment based on C3 data classification. | Development and Implement
h | Update logging facilities | update logging: - storage - reporting - analyse | Research;
i | Update logging facilities | update logging: - storage - reporting - analyse | backbone deployment
j | Implementation of PAC file webservers | Move PAC files from Proxy servers to alternate infrasture/location | Development
k | Implementation of PAC file webservers | Move PAC files from Proxy servers to alternate infrasture/location | Backbone deployment
l | Implementation of PAC file webservers | Move PAC files from Proxy servers to alternate infrasture/location | Release
13 | SWE: CEDS rollout SWE | Rollout of CEDS in SWE, branch BE, I, CH, SP, Lux, P, Fr |  | q1 | q4 | on schedule
a | CEDS rollout in Branches BE | CEDS in Branches BE | CEDS in Branches BE
b | CEDS at EuroBank Bank Germany phase II | CEDS at EuroBank Bank Germany phase II (DRS, Chinese Walls) | CEDS at EuroBank Bank Germany phase II
c | CEDS in Luxemburg | CEDS in Luxemburg
d | CEDS in Switzerland | CEDS in Switzerland
e | CEDS in Italy | CEDS in Italy
f | CEDS in Spain | CEDS in Spain
g | CEDS in Portugal | CEDS in Portugal
14 | SWE: Central e-mail hosting CE | Host e-mail of 6 eastern european countries in Brussel |  | q3 | q2-07 | not started yet, likely to be moved to Poland
a | Consolidation e-mail | Ongoing project: consolidation, exchange 2003, legal mail archiving. | For 2006: Change Migration of users and phase out old infrastructure
15 | Ironport | European operational management of e-mail security facility |  | q3 | q4 | started
a | Geo Fail over internet mail NL/SWE | Setup a GEO Fail over for internet mail between NL and SWE | Development and Implement
16 | SWE: Ugrade to exchange 2003 SWE | Already promised to business, Allign with NL exchange program |  | q2 | q4 | on schedule
17 | C3 Secure Mail | Implementing retention periods for mail archiving |  | q2 | q4/q1-07 | base ready, on schedule
a | Develop C3/C4 data storage | Develop and implement the option to store C3/C4 classified files | Development
b | Research signing external mail | Research default signing of external messages | Research: helps to improve EuroBank's integrity
c | Implement secure mail product | Make secure mail possible on larger scale by using PKI certificates | Change: implement PKI certificates for secure mail
18 | Call centre retail maintenance | Retail operates a call centre which is supported by It Infra. Some maintenance and possibly further development is required | - Develop - Implement | q1 | q4/q1-07 | on schedule
a | Upgrade Callcenter Retail naar release CM 4 | Upgrade Avaya environment to latest release | change
b | Upgrade Symon application IBN | expansion of wallboards only possible with new wallboards | change
c | Replacement of Siebel 6 | The successor of Siebel 6, either Siebel 7, or new Websphere application (this choicewill be made by Retail) will have impact on the callcenter infra, especially on CTI | change
d | Upgrade SMS Saldo
e | Migrate VRO (Voice Response Ordering) VRU's and BOL to Intervoice | Current Comsys VRU's for VRO are end-of life, migrate them to the standard Intervoice IVR's including VoiceXML application | Standardisation
f | Migrate IBN Saldolijn to Intervoice | Current Comsys VRU's for IBN Saldolijn are end-of life, migrate them to the standard Intervoice IVR's including VoiceXML application | Standardisation
g | Migrate VRU's Postbank Verzekeringen to Intervoice | Current Comsys VRU's for Postbank Verzekeringen are end-of life, migrate them to the standard Intervoice IVR's including VoiceXML application | Standardisation
h | Migrate EuroBank HR Ziekmeldlijn to Intervoice | Current Comsys VRU for EuroBank HR Ziekmeldlijn are end-of life, migrate them to the standard Intervoice IVR's including VoiceXML application | Standardisation
i | Migrate RVS VRU to Intervoice | Current Avaya Conversant VRU is end-of-life, migrate them after project ''Upgrade callcenter Retail'' to Intervoice including application | Standardisation
j | Upgrade MTC | Upgrade Intervoice Isoft IVR's to MTC (conditional for project ASR rollout Telefoonbank) | Upgrade / change
k | AAP (Automated Agent Platform) Voice Response Content Management System | Develop and IVR Content Management System for Telefoonbank Functioneel beheer | Development
l | ASR rollout Telefoonbank | Implementation of speech recognition servers for Telefoonbank | change
m | Upgrade IVR management systems to Control Center | Implement successor of current Intervoice Management tools | Upgrade / change
n | Avaya Interaction Center | Implement successor of Avaya CT 1.3, probably conditional for ''project Replacement Siebel 6'' | Upgrade / change
o | Nice Quality Monitoring | Voice and Screen logging in callcenter | Change
p | Callgenerator with ASR capabilities | Needed for testing the speech ASR applications for Telefoonbank | Development
q | Upgrade Nice callcenter | Current releases are no longer supported form a release management point of view, also some Windows NT4 servers have to be upgraded | change
r | Central storage Nice Retail | Store call data centrally instead of locally on tape- or DVD-drives. This solves the current issues with the large number of tape/DVD drive problems | change
19 | Mail migration APAC / LATAM | Upgrade mail infra in APAC/LATAM to the current standard. | - Localise - Change | q1 | q4 | on schedule
20 | Print exit | Reduce the number of printers with 30% (from 5000 to 3500). Replace old printers to avoid high maintenance costs | - decomission old - purchase new - install new | q2 | q4/q1-07 | project waiting for EuroBank NL approval
21 | Entitlement | Only new development is included. Version changes, capacity upgrade are considered as baseline activities and are included in other related initiatives bundled for all other WPS-owned technologies |  | q1 | q4-07 | difficult
a | ITIM support contract ITIM and IDI | Buy in of ITIM specialist knowledge to assist 3th level support, advice on usage of new functionality and to intermediare to IBM organsation for follow-up of problem and enhancement requests | development / Backbone deployment / change
b | Disaster recovery extension | Adopt disaster reovery to accomodate new functionality (connected platforms, RB0x, new hardware, new IITM version) | change
c | extend Reporting Developing | In order to comply to legal and EuroBank internal regulations reporting base need to extended (this part concerns changes on ITM and DB to supply required input data to Business Objects reporting) | Development
d | extend Reporting Implementation | In order to comply to legal and EuroBank internal regulations reporting base need to extended (this part concerns changes on ITM and DB to supply required input data to Business Objects reporting) | Change
e | Performance improvement monitoring and facilities for technical management | In order to improve operational and technical support monitoring need to be extended and tooling need to be added | development
f | Performance improvement monitoring and facilities for technical management | In order to improve operational and technical support monitoring need to be extended and tooling need to be added | change
g | new agents | Upon request of WPS additional existing types of server (e.g. HP NonStop) and application systems (e.g. Oracle, SAP, Siebel, Peoplesoft) need to be connected to ITIM to govern userids and authorisations and to accomodate automatic provisioning of roles. | development
h | functionality existing agents | To accomodate full support of automatic provisioning functionality of existing agents need to be extended (new attributes, replacement to IDI based agents) | Backbone deployment / Change
i | functionality EAA | EAA = end user interface for authorisation requests and password management. New functionality will be required (additonal forms, dialogues improvement, additional languages) | development
j | maintenance EAA | EAA = end user interface for authorisation requests and password management. Baseline activity for maintenance of the existing functionality | change
k | HR feed new CDS (GDIL) | Due to introducntion of GDIL the current CDS MetaDirectory feed will change. | Backbone deployment / Change
l | functionality RBOX | Rbox = enduser interface for management of Roles and Assets. New functionality need to be added (dialogue improvement, additional internal security, improvement request based upon true production usage, presentation of role-tree) | development
m | maintenance RBOX | Rbox = enduser interface for management of Roles and Assets. Baseline activity for maintenance of the existing functionality | change
n | Migration Entitlement Infrastructure to RSABB | Migration Entitlement Infrastructure to RSABB | change
o | entitlement, finishing | phase out activities of entitlement. Main job being done in 2005. | infrastructure new releases, fininshing TAM
p | entitlement, implementation | managing the implementation in the LOB's, for as far as not covered in 2005 | implementation, building release 4
q | Upgrade ITIM Hardware | Due to expected growth of ITIM load AIX and SUN server will require upgrade | change
22 | Handheld workstation | Develop a standard EuroBank solution for a handheld workstation allowing for efficient personal productivity (office, mail, browsing, collaboration, etc). | - Research - Develop standard - Implement new service | q2 | q4 | from POC to pilot, to project(with PST help)
a | Develop a EuroBank policy for (use of) Mobile devices. | A policy is an absolute must if we want to start with mobile solutions. This should be created as the basis on which we can build our (future) solutions. | Development
b | Handheld workstation | Investigate options for a mobile desktop (PDA, mail, etc). There are multiple technologies eveloving and competing. Currently there is no standard within EuroBank. The outcome: overall approach, architecture and building blocks. | Research
23 | CEDS Workplace Migration NL | last part CEDS Workplace Migration NL |  | q1 | q4 | almost finished
24 | CEDS Release 2.3.x | CEDS release |  | q1 | q2-07 | controlled within ITT Progam outside SWS, WPS delivers capacity
25 | SWE: Hosting EuroBank France | Hosting EuroBank France - end users fully supported (hosted from Brussels) |  | q2 | q3/q4 | on schedule
26 | Legacy IT Infra | projects controlled and steered by the ITT program : Citrix upgrade, Telephony Legacy Migration(wintel based servers), DRP SWE, Legacy SWE Email | reduce legacy | q2 | q4/q2-07 | controlled within ITT Progam outside SWS, WPS delivers capacity
27 | Non personal Account Support by ITIM | build of ITIM support |  | q2 | q2/07 | off schedule
28 | SRP Phase 2 | invulling en cooperatie tav Strategisch Ruimte Plan |  | q2 | q4-2007 | project control to Facility Managementl
29 | SWE: SWESAC | implementation of SWE CEDS SPOC procedure kit |  | q1 | q4 | on schedule
30 | SWE: Fairdisp | Reduce the number of printers, analyse periph. and develop policy. Replace |  | q1 | q4 | on schedule
31 | SWE: Call Flow Management Belgium | 300/575 rolled our |  | q2 | q4 | on schedule
32 | SWE: integration and /migration of Lux Mail enviroment |  |  | q2 | q4 | on schedule
Note on B44: Marcel van Essen: Samenvoeging van Corporate key Login, 1 kerberos realm, and strong authentication. In samenspraak met Co Viezee.
Note on B122: Marcel van Essen: It's not clear to me who should initiate this. We are functional owner of the technical infrastructure but not of the functionality. That is owned by a different party. They should, in my opinion, initiate the introduction of the new needed functionality (= agent), They have to claim the resources in there MTP. We decided to ad this line anyway to be sure that it isn't forgotten.
Note on B124: Marcel van Essen: More or Lese the same note as item "new agents"
Note on B127: Marcel van Essen: More or Lese the same note as item "new agents"

## Non Baseline Projects > CD
Notes: This tab is an extract from the "EuroBank-Requested Projects". Only currently running non-baseline projects are included in this tab. Columns H, I, J are new and added: H contains additional new information, I contains best EuroBank estimates on required SWS manhrs after CD, K contains best EuroBank estimates for investments. THIS TAB IS FOR INFORMATION PURPOSES ONLY!
CD assumed 01Feb07
Nr | Project name | Project Description | High Level project activities | startdate | expected to end | remarks/status | Comments 22Nov06 | EuroBank estimated budget wrt SWS resources | EuroBank estimated budget wrt investments
2 | Maintain office telephony | Replace depreciated and not performing office telephony and call logging equipment with the current standard. Upgrade capacity meeting growing demand. Improve quality of GSM coverage | - purchase new equipment - change management - decomission the old equipment | q1 | q4 | on schedule
c | Phase out old equipment Alcatel Leeuwarden and Haarlemmerweg | Old releases of PABX's some only best effort | change |  |  |  | (1) Haarlemmerweg planned for Sep 07 (2) Leeuwarden planned q1-07 => No project plans available for these activities | Not available | Not available
g | SRP | strategic space plan FM requirements |  |  |  |  | See item 28 below "SRP Phase 2" | See item 28 | See item 28
9 | NetIQ fase 2 | Develop and deploy security monitoring and management tooling for AD. | -Research - Develop - Deploy/upgrade central infra | q3 | q4 | started, fase 1 ended | Planned completion 2007 - 03 | ≤ 25k | Not applicable
10 | Develop services on CIA levels 3 | Customers are requesting security and availability levels which are higher then the current standard for workplace (C2I2A2). Achieving higher levels requires changes in technology, procedures and possibly organisation | - Develop - Implement - Deploy backbone | q3 | q4/q1-07 | on schedule | Planned completion 2007 - 04 | ≤ 25k | Not applicable
13 | SWE: CEDS rollout SWE | Rollout of CEDS in SWE, branch BE, I, CH, SP, Lux, P, Fr |  | q1 | q4 | on schedule
c | CEDS in Luxemburg | CEDS in Luxemburg |  |  |  |  | Planned completion 2007 - 03 | ≤ 25k | Not applicable
d | CEDS in Switzerland | CEDS in Switzerland |  |  |  |  | Planned completion 2007 - 03 | ≤ 25k | Not applicable
e | CEDS in Italy | CEDS in Italy |  |  |  |  | Planned completion 2007 - 03 | ≤ 25k | Not applicable
15 | Ironport | European operational management of e-mail security facility |  | q3 | q4 | started | Planned completion 2007 - 03 | ≤ 25k | Not applicable
16 | SWE: Ugrade to exchange 2003 SWE | Already promised to business, Allign with NL exchange program |  | q2 | q4 | on schedule | Planned completion 2007 - 02 | ≤ 25k | Not applicable
18 | Call centre retail maintenance | Retail operates a call centre which is supported by It Infra. Some maintenance and possibly further development is required | - Develop - Implement | q1 | q4/q1-07 | on schedule
b | Upgrade Symon application IBN | expansion of wallboards only possible with new wallboards | change |  |  |  |  | ≤ 25k | Not applicable
c | Replacement of Siebel 6 | The successor of Siebel 6, either Siebel 7, or new Websphere application (this choicewill be made by Retail) will have impact on the callcenter infra, especially on CTI | change |  |  |  | This is part of the TOSCA program from Postbank. This program is expected to run through to 2009. Exact figures for SWS manhrs and investments not known. | Not available | Not available
n | Avaya Interaction Center | Implement successor of Avaya CT 1.3, probably conditional for ''project Replacement Siebel 6'' | Upgrade / change |  |  |  | This is now part of TOSCA "plateau" 3. No further information available as to project plans, etc.. | Not available | Not available
q | Upgrade Nice callcenter | Current releases are no longer supported form a release management point of view, also some Windows NT4 servers have to be upgraded | change |  |  |  |  | ≤ 25k | Not applicable
21 | Entitlement | Only new development is included. Version changes, capacity upgrade are considered as baseline activities and are included in other related initiatives bundled for all other WPS-owned technologies |  | q1 | q4-07 | difficult | Current running activities will cross CD. Additional work is planned but no decisions as yet made on them; expected additional 5-7M. | 500k | Not available
24 | CEDS Release 2.3.x | CEDS release |  | q1 | q2-07 | controlled within ITT Progam outside SWS, WPS delivers capacity | This is the "Build 19" project. | 210k | Not applicable
26 | Legacy IT Infra | projects controlled and steered by the ITT program : Citrix upgrade, Telephony Legacy Migration(wintel based servers), DRP SWE, Legacy SWE Email | reduce legacy | q2 | q4/q2-07 | controlled within ITT Progam outside SWS, WPS delivers capacity | No budget data provided by PM. | 34 FTE | Not available
28 | SRP Phase 2 | invulling en cooperatie tav Strategisch Ruimte Plan |  | q2 | q4-2007 | project control to Facility Managementl |  | 690k | 2,3M
30 | SWE: Fairdisp | Reduce the number of printers, analyse periph. and develop policy. Replace |  | q1 | q4 | on schedule | Planned completion 2007 - 03 | ≤ 25k | Not applicable

## Agreed LAN Baseline Projects
Baseline
| Country | Activity | startdate | enddate | status | AO | GTN | TelCo
LCM | NL+B | Multi cast | 2007 | 2007 | ongoing | Not applicable | Not applicable | This activity is within TelCo's base charge.
LCM | B | Obsolete LAN devices in CSM/MX LAN +data center | 2006 |  | exe | Not applicable | Not applicable | In principal this activity is within the base charge of TelCo if these are assets that TelCo will take ownership of. However for running projects TelCo will consider renewal projects of this equipment between Effective Date and Commencement Date the responsibility of EuroBank. Therefore these activities are not in the base charge. After commencement date TelCo will be responsible for this kind of renewal and therefore will decide which equipment should be renewed. In case TelCo decides that renewal is necessary, the renewal will be done within the Base Charge.
LCM | B | Obsolete LAN devices in belgian branches | 2006 |  | exe | Not applicable | Not applicable | In principal this activity is within the base charge of TelCo if these are assets that TelCo will take ownership of. However for running projects TelCo will consider renewal projects of this equipment between Effective Date and Commencement Date the responsibility of EuroBank. Therefore these activities are not in the base charge. After commencement date TelCo will be responsible for this kind of renewal and therefore will decide which equipment should be renewed. In case TelCo decides that renewal is necessary, the renewal will be done within the Base Charge.
LCM | B | Obsolete LAN devices in belgian subsidaries | 2006 |  | exe | Not applicable | Not applicable | In principal this activity is within the base charge of TelCo if these are assets that TelCo will take ownership of. However for running projects TelCo will consider renewal projects of this equipment between Effective Date and Commencement Date the responsibility of EuroBank. Therefore these activities are not in the base charge. After commencement date TelCo will be responsible for this kind of renewal and therefore will decide which equipment should be renewed. In case TelCo decides that renewal is necessary, the renewal will be done within the Base Charge.

## Agreed Baseline Projects
Nr | Project name | Project Description | High Level project activities | startdate | expected to end | remarks/status | AO | GTN | TelCo
1 | Datacenter-based HW renewal due to depreciation | Renew solution based on the current standard for HW and SW due to depreciation of HW | - Purchase HW/SW - Deploy - Decomission old |  |  | ongoing | Activities required for in scope server HW refresh (excl. upgrades and/or changes for business applications) are part of the Base Charges. | Costs included in Base Charges only if related to refresh activities in the scope of Vendor Gamma. | In principal this activity is within the base charge of TelCo if these are assets that TelCo will take ownership of. However for running projects TelCo will consider renewal projects of this equipment between Effective Date and Commencement Date the responsibility of EuroBank. Therefore these activities are not in the base charge. After commencement date TelCo will be responsible for this kind of renewal and therefore will decide which equipment should be renewed. In case TelCo decides that renewal is necessary, the renewal will be done within the Base Charge.
3 | Server OS versions upgrade | Migrate Wintel servers to the current release | Change | q1 | q4 | controlled within ITT Progam outside SWS, WPS delivers capacity | Base unless < N-1; excluding cost Appl change | Not applicable | Not applicable
4 | Server Windows OS major changes | Major changes to the windows server OS affecting applications running on top | - Release |  |  | ongoing | Base unless < N-1; excluding cost Appl change | Not applicable | Not applicable
5 | Office-based computer HW renewal due to depreciation | Renew solution based on the current standard for HW and SW due to depreciation of HW | - Purchase HW/SW - Deploy - Decomission old |  |  | ongoing | Not applicable | Costs included in Base Charges only if related to refresh activities in the scope of Vendor Gamma. | Not applicable
6 | Workstation Windows OS major changes | Major changes to the workstation OS affecting applications running on top | - Release |  |  | ongoing | Base unless < N-1; excluding cost Appl change | Not applicable | Not applicable